## Summary
CITRIX WORKSPACE AUTOMATION SUITE
Use Case Detailed Assessment — Effort, Resources & Operational Steps
◼ USE CASE INDEX
ID | Use Case Title | Effort | Resources | Priority | Complexity | Steps
UC-01 | Citrix Application Onboarding Automation | 6–8 hrs per application | 2 Citrix Engineers, App Packaging Tools, Test VDA Pool | High | Medium | 6
UC-02 | Desktop Publishing Automation (VC Desktop) | 3–4 hrs per desktop publishing cycle | 1 Citrix Engineer, Citrix Studio, MCS/PVS Infrastructure | High | Low | 6
UC-03 | Studio Policy Automation | 2–3 hrs per policy update | 1 Citrix Engineer, AD Team (for GPO coordination) | Medium | Medium | 6
UC-04 | Layer Transfer Between Regions | 4–6 hrs per transfer (quarterly / semi-annual) | 1–2 Senior Citrix Engineers, ACT Tool, PowerShell SDK, Network / Infra Team | High | High | 6
UC-05 | Weekly User Log & GPO Compliance Review | 2–3 hrs per week (recurring) | 1 Ops Engineer, GPMC, Citrix Director, ITSM Tool | Critical | Medium | 7
◼ KEY METRICS
Total Use Cases | Weekly Effort Est. | Engineers Required | Total Steps Defined | Overall Priority
5 | 17–29 hrs | 3–5 | 32 | High
CONFIDENTIAL — For Internal Leadership Use Only ¦ Citrix Infrastructure & Automation Team

## UC-01
CITRIX WORKSPACE AUTOMATION SUITE — DETAILED USE CASE
UC-01 ¦ Citrix Application Onboarding Automation
⏱ Effort: 6–8 hrs per application |  | 👥 Resources: 2 Citrix Engineers, App Packaging Tools, Test VDA Pool |  | 💡 Priority / Complexity: High / Medium
🏆 Business Value: Accelerates application delivery, reduces manual effort, improves consistency
Step | Operational Activity | Detailed Step Description | Owner / Role | Tool / System Used | Output / Artefact
1 | Collect application requirements | Gather functional and non-functional requirements, security constraints, and target user groups from business requestors via service desk ticket or intake form. Document supported OS versions, install switches, licensing mode, and application dependencies. | Ops Engineer | ServiceNow / Jira | Requirements Document
2 | Package the application | Build the application package using Citrix App Layering (for layer-based delivery) or MSI/MSIX standard packaging. Validate installer behaviour in an isolated sandbox environment. Handle registry entries, shortcuts, COM objects, and service dependencies. | Citrix Engineer | App Layering / MSI Studio / PSADT | Application Package / Layer
3 | Validate compatibility with VDAs | Deploy the package to a test VDA pool. Verify application behaviour: DLL conflicts, registry collisions, multi-session compatibility, and profile interaction. Run App-V or App Layering compatibility matrix checks against the VDA OS baseline. | Citrix Engineer | VMware vSphere / Citrix VDA | Compatibility Test Report
4 | Publish app via Citrix Studio / Web Studio | Create or update Application objects in Citrix Studio or Web Studio. Assign to the appropriate Delivery Group, configure working directory, command-line parameters, icon path, and user visibility settings (group filter or direct assignment). | Citrix Engineer | Citrix Studio / Web Studio | Published Application Object
5 | Test delivery to pilot users | Validate end-to-end delivery to a defined pilot user group through Citrix Workspace or StoreFront. Confirm SSO authentication, printing, clipboard redirection, drive mapping, USB device access, and session reliability under concurrent load. | QA / Pilot Users | Citrix Director / Workspace | Pilot Sign-off Report
6 | Document onboarding steps and close change | Log all onboarding steps in the CMDB and ITSM platform. Create a runbook document including packaging steps, compatibility evidence, known issues, and rollback procedure. Attach to the change record for compliance and audit review. | Citrix Engineer | CMDB / Confluence / ITSM | Runbook & Audit Log
CONFIDENTIAL — For Internal Leadership Use Only ¦ Citrix Infrastructure & Automation Team

## UC-02
CITRIX WORKSPACE AUTOMATION SUITE — DETAILED USE CASE
UC-02 ¦ Desktop Publishing Automation (VC Desktop)
⏱ Effort: 3–4 hrs per desktop publishing cycle |  | 👥 Resources: 1 Citrix Engineer, Citrix Studio, MCS/PVS Infrastructure |  | 💡 Priority / Complexity: High / Low
🏆 Business Value: Increases operational efficiency, reduces turnaround time, supports faster user onboarding
Step | Operational Activity | Detailed Step Description | Owner / Role | Tool / System Used | Output / Artefact
1 | Create Machine Catalog in Citrix Studio | Define a new Machine Catalog in Citrix Studio. Select the provisioning method (MCS or PVS), choose the master image snapshot, configure the VM naming scheme convention, and set the target number of virtual machines. Assign the appropriate hosting connection and resource zone. | Citrix Engineer | Citrix Studio / MCS / PVS | Machine Catalog
2 | Assign desktops to Delivery Groups | Create or update Delivery Groups and assign the new Machine Catalog. Configure user assignment rules (Active Directory group or direct user assignment), set maximum session limits, and apply power management schedules aligned to business hours. | Citrix Engineer | Citrix Studio | Delivery Group Configuration
3 | Configure Citrix policies for VC desktop | Apply Citrix policies tailored to VC desktop use cases: bandwidth allocation, audio quality, USB device redirection, printer redirection, and client drive mapping. Validate settings against the baseline policy template approved by IT governance. | Citrix Engineer | Citrix Studio / Group Policy | Policy Configuration Record
4 | Publish desktops to end users | Enable desktop access through Citrix StoreFront and the Workspace portal. Set user-facing display names, descriptions, and icons for clarity. Configure desktop launch settings, preferred client detection rules, and session pre-launch options. | Citrix Engineer | StoreFront / Workspace | Published Desktop
5 | Validate access and performance | Log in as a representative test user and measure logon time, profile load duration, desktop responsiveness, and peripheral redirection (printers, drives, USB). Confirm results are within SLA thresholds defined in the desktop service specification. | Citrix Engineer | Citrix Director / Performance Monitor | Performance Validation Report
6 | Document publishing activity | Record the publishing change in the ITSM platform with all configuration details. Update the infrastructure register with catalog size, master image version, hypervisor zone, Delivery Group membership, and applied power management schedule. | Citrix Engineer | ITSM / Infrastructure Register | Infrastructure Record
CONFIDENTIAL — For Internal Leadership Use Only ¦ Citrix Infrastructure & Automation Team

## UC-03
CITRIX WORKSPACE AUTOMATION SUITE — DETAILED USE CASE
UC-03 ¦ Studio Policy Automation
⏱ Effort: 2–3 hrs per policy update |  | 👥 Resources: 1 Citrix Engineer, AD Team (for GPO coordination) |  | 💡 Priority / Complexity: Medium / Medium
🏆 Business Value: Standardises governance, improves compliance posture, reduces misconfiguration risk
Step | Operational Activity | Detailed Step Description | Owner / Role | Tool / System Used | Output / Artefact
1 | Define governance policies with stakeholders | Collaborate with IT Governance and Security teams to define required Citrix policies covering: printer redirection, bandwidth limits, clipboard access restrictions, drive mapping, USB device policy, and session time-out rules. Obtain formal written approval from the policy owner before proceeding. | IT Governance / Security | ServiceNow / Policy Register | Policy Design Document
2 | Configure policies in Citrix Studio | Create or update policy objects in Citrix Studio or Web Studio. Set filter conditions to scope policies correctly: by AD user group, Delivery Group name, IP subnet range, or client device type. Assign priority order to control precedence within the Citrix policy engine. | Citrix Engineer | Citrix Studio / Web Studio | Citrix Policy Objects
3 | Resolve precedence conflicts with AD GPOs | Review and document conflicts between Citrix Studio policies and Active Directory Group Policy Objects. Use the Group Policy Modeling Wizard in GPMC to simulate effective policy for representative user/computer combinations. Document precedence decisions in the policy conflict matrix. | Citrix / AD Engineer | GPMC / Group Policy Modeling Wizard | Policy Precedence Matrix
4 | Test policy application on pilot VDAs | Apply policies to a pilot VDA set. Use the Citrix Policy Simulator in Studio and GPMC Resultant Set of Policy (RSoP) to verify effective settings match the designed intent. Test with multiple user accounts representing different AD groups and device types. | Citrix Engineer | Citrix Studio Simulator / RSoP | Test Evidence Screenshots
5 | Document policy changes for compliance | Record all policy changes in the policy change log with before/after comparison, business justification, approver name, and implementation date. Attach test evidence and GPM output to the change ticket to maintain a complete audit trail. | Citrix Engineer | ITSM / Audit Tracker | Compliance Change Log
6 | Roll out policies to production | After successful pilot sign-off, apply updated policies to all production Delivery Groups. Communicate changes to the helpdesk team with a clear summary of expected user-facing behaviour changes. Monitor Citrix Director for any session or policy-related incidents within the first 48 hours post-deployment. | Citrix Engineer | Citrix Studio / Director | Production Policy / Incident Watch
CONFIDENTIAL — For Internal Leadership Use Only ¦ Citrix Infrastructure & Automation Team

## UC-04
CITRIX WORKSPACE AUTOMATION SUITE — DETAILED USE CASE
UC-04 ¦ Layer Transfer Between Regions
⏱ Effort: 4–6 hrs per transfer (quarterly / semi-annual) |  | 👥 Resources: 1–2 Senior Citrix Engineers, ACT Tool, PowerShell SDK, Network / Infra Team |  | 💡 Priority / Complexity: High / High
🏆 Business Value: Ensures DR resilience, supports disaster recovery readiness, avoids potential downtime losses
Step | Operational Activity | Detailed Step Description | Owner / Role | Tool / System Used | Output / Artefact
1 | Export site configuration using ACT | Use the Citrix Automated Configuration Tool (ACT) to export the source CVAD site configuration. Capture Delivery Groups, Machine Catalogs, Application objects, Citrix Policies, and Administrative Delegations as structured YAML files. Version-tag the export with the date, operator name, and source site identifier. | Senior Citrix Engineer | Citrix ACT Tool | YAML Configuration Export
2 | Validate YAML files for errors and dependencies | Review exported YAML files using ACT's built-in validation and a schema linter (VS Code with YAML extension). Check for unresolved resource references (hosting connections, zone names, image snapshot paths). Correct region-specific paths, machine naming conventions, and storage configurations that differ between source and target regions. | Senior Citrix Engineer | ACT YAML Validator / VS Code | Validated YAML Files
3 | Import configuration into target region | Execute the configuration import against the target CVAD site using the Citrix PowerShell SDK or REST API. Map source resource locations (hosting connections, storage repositories, hypervisor zones) to their target region equivalents. Run the import in dry-run (preview) mode first to identify mapping errors before committing changes. | Senior Citrix Engineer | Citrix PowerShell SDK / REST API | Imported Site Configuration
4 | Perform smoke tests in target region | Launch a representative set of applications and desktops from the target region via Citrix Workspace. Validate session connectivity, SSO authentication through StoreFront, Citrix policy application, printer redirection, and drive mapping. Test with user accounts from both standard and privileged AD groups. | QA / Citrix Engineer | Citrix Director / Workspace App | Smoke Test Report
5 | Update DR documentation and audit logs | Update the Disaster Recovery runbook to reflect the new target region configuration including updated recovery time objectives (RTOs), resource location references, and revised step-by-step recovery procedure. Log the transfer event in the infrastructure audit trail with operator name, timestamp, and smoke test outcomes. | Citrix Engineer | Confluence / ITSM / DR Tracker | Updated DR Runbook & Audit Log
6 | Coordinate infrastructure and network validation | Confirm all supporting infrastructure in the target region is correctly configured: Citrix ADC (NetScaler) virtual servers and policies, StoreFront server group replication status, firewall rules for ICA/HDX traffic (TCP 443, 1494, 2598), DNS resolution for delivery controllers and licensing server, and license server accessibility from VDAs. | Network / Infra Team | NetScaler / DNS / Firewall Console | Network Validation Report
CONFIDENTIAL — For Internal Leadership Use Only ¦ Citrix Infrastructure & Automation Team

## UC-05
CITRIX WORKSPACE AUTOMATION SUITE — DETAILED USE CASE
UC-05 ¦ Weekly User Log & GPO Compliance Review
⏱ Effort: 2–3 hrs per week (recurring) |  | 👥 Resources: 1 Ops Engineer, GPMC, Citrix Director, ITSM Tool |  | 💡 Priority / Complexity: Critical / Medium
🏆 Business Value: Strengthens audit readiness, prevents compliance penalties, ensures consistent policy enforcement
Step | Operational Activity | Detailed Step Description | Owner / Role | Tool / System Used | Output / Artefact
1 | Collect VDA event logs from all servers | Aggregate Windows Event Logs and Citrix Director session data from all production VDA pools using a PowerShell log collection script. Pull Application, System, and Security event logs. Filter for relevant Event IDs: logon failures (4625), session disconnects, Group Policy application events (1500–1503), and Citrix broker connection failures. | Ops Engineer | PowerShell / Event Viewer / Citrix Director | Log Collection Archive
2 | Run Group Policy Modeling Wizard simulations | In the Group Policy Management Console (GPMC), run the Group Policy Modeling Wizard for representative user/computer combinations across all affected VDA Organisational Units (OUs). Capture the simulated effective policy for each scenario. Export results as HTML reports and archive them for the compliance record. | Ops Engineer | GPMC / Group Policy Modeling Wizard | GPM Simulation Reports
3 | Compare Citrix Studio policy vs AD GPO effective settings | Cross-reference Citrix Studio policy effective settings (from Policy Simulator) against GPM simulation results for the same users. Map each Citrix policy setting against the corresponding Active Directory GPO setting. Identify where Citrix policies override, complement, or conflict with AD GPOs for each key configuration area. | Ops Engineer | Citrix Studio / GPMC / RSoP | Policy Comparison Analysis
4 | Identify and categorise policy conflicts | Flag policy conflicts across key functional areas: printer redirection, client drive mapping, clipboard access, USB device policy, session time-out settings, and audio quality. Categorise each conflict by severity (blocks user workflow = High, minor deviation = Low) and by the size of the affected user population. | Ops Engineer | Citrix Director / GPMC | Conflict Register (Severity Rated)
5 | Escalate conflicts to the AD team via ITSM | Raise each confirmed policy conflict as a formal ITSM service request assigned to the Active Directory team. Include in each ticket: affected user population, conflicting policy settings (both Citrix and AD), observed versus expected user behaviour, supporting evidence (screenshots/logs), and proposed resolution approach. Agree ownership and target resolution date. | Ops Engineer → AD Team | ServiceNow / ITSM Platform | ITSM Escalation Tickets
6 | Update the weekly audit compliance tracker | Record the week's findings in the compliance tracker (GRC tool or spreadsheet). Update the status of open items from prior weeks (Resolved / Outstanding / Escalated). Attach evidence screenshots for items being closed. Maintain running metrics: total open conflicts, mean time to resolution (MTTR), and repeat violation count. | Ops Engineer | Excel / GRC Tool / Confluence | Updated Compliance Tracker
7 | Distribute weekly governance report | Prepare the weekly compliance summary report. Include: executive summary of findings, open versus resolved conflict counts, any critical or new high-severity findings, trend charts (3-week rolling), and outstanding risk items with owners and due dates. Distribute to IT Governance, CISO team, and relevant Delivery Managers via email or the shared compliance portal. | Ops Engineer / IT Manager | Email / SharePoint / ITSM Reporting | Weekly Governance Report
CONFIDENTIAL — For Internal Leadership Use Only ¦ Citrix Infrastructure & Automation Team