## Meeting Action Items
Citrix Operations – Meeting Minutes / Action Items
Participants: Anil, Raghavendra, Mani ¦ Date: 28–29 July 2026
Action Item | Owner | Status | ETA | Comments
Camunda Portal – Citrix Catalog Access | Anil & Team | Pending | 29-Jul-2026 | Please confirm access for all members of the Ops team and ensure this is resolved as soon as possible.
Collect additional monitoring parameters for the Health Check report; evaluate Service Restart Automation and any new use cases | Raghavendra | Pending | 29-Jul-2026 | Kindly share the requested information by end of day.
Daily Checklist in Panorama and Palo Alto Firewall | Mani & Team | Completed | 28-Jul-2026 | As discussed on the call, these daily updates are now redundant, as they do not provide real-time status. This checklist was originally introduced because, at the time the services went live, there was no mechanism in place to monitor these health checks. A health and alert management email system is now in place that meets this requirement in real time. We therefore request that these daily updates be discontinued from Operations, and this use case be marked as cancelled.